## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2231-swen-261-10-04 GuessN'Check
Testing Team Name | 2231-swen-261-10-03

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Helper, I want to see a list of needs so that I choose which ones to fulfill. | Given that I am on the u-fund site, when I look for needs then I expect a place to see available needs. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given that I am on the u-fund site, when the manager creates a new need, then I expect to see it on the Needs page. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
As a Helper, I want to checkout with my funding basket to fulfill all needs I have chosen. | Given I am on the u-fund site, when I view my basket, then I expect a checkout option. | Pass | BF; 10/30/2023 | Pass | CW; 11/13
| Given I have checked out, when I view my basket, then I expect it to be empty. | Pass | RL; 10/30/2023 | Pass | CW; 11/13
| Given I have checked out, when I view all needs, then I expect to see the needs I funded to reflect my funds. | Pass | RL; 10/30/2023 | Pass | CW; 11/13
As a Helper, I want to add needs from my funding basket to group needs I want to fulfill. | Given I am in the u-fund site, when I browse needs, then I expect to be able to add a need to my funding basket. | Pass | MF; 10/29/2023 | Pass | CW; 11/13
| Given I am in the u-fund site, when I add a need to my basket, then I expect an indicator that the operation was successful. | Pass | MF; 10/29/2023 | Pass | MF; 11/19
As a Helper, I want to remove needs from my funding basket as to not fund them upon checkout. | Given I am in the u-fund site, when I view my basket, then I expect to find an indicator to remove a need from the basket. | Pass | MF; 10/29/2023 | Pass | CW; 11/13
| Given I am viewing my basket, when I delete a need, then I expect the basket to reflect the change. | Pass | MF; 10/29/2023 | Pass | CW; 11/13
As a Helper, I want to view needs in my funding basket to know the needs I plan on fulfilling. | Given I am on the u-fund site, when I am logged in, then I expect to see a way to access my funding basket. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given I am on the u-fund site, when I access my basket, then I expect to see the needs I have added to it. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given that I am viewing my basket, when I have made changes to it, then I expect the changes to be reflected in my basket. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
As a User, I want to authenticate to access features related to my role. | Given I am a user when I access the software then I expect to be asked for my credentials (can be username only) | Pass | NZ; 10/30/2023 | Pass | CW; 11/13 | notification for failed login??
| Given I am a Helper when I attempt to log in then I expect to be treated as a Helper by the software. | Pass | NZ; 10/30/2023 | Pass | CW; 11/13
| Given I am a Helper when I have logged in then I expect to see only my funding basket (not others' baskets). | Pass | NZ; 10/30/2023 | Pass | CW; 11/13
| Given I am a Manager when I attempt to log in then I expect to be treated as a Manager by the software. | Pass | NZ; 10/30/2023 | Pass | CW; 11/13
As a Manager, I want to remove needs from my cupboard to no longer display them to Helpers. | Given I am viewing my cupboard when I see a need then I expect to be able to delete it. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given I am viewing my cupboard when I have deleted a need then I expect my cupboard to no longer show it. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given a need has been deleted when a Helper browses needs then I expect the deleted need to no longer be visible. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
As a Manager, I want to view needs in my cupboard to see the needs I am advertising and their status. | Given I am a Manager when I use the software then I expect to be able to access my cupboard. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
| Given I am a Manager when I view my cupboard then I expect to see all the needs it contains. | Pass | MF; 10/30/2023 | Pass | CW; 11/13
As a Manager, I want to add/edit the data related to a need in my cupboard to update the information displayed to helpers regarding the need. | Given I am a Manager when I view my cupboard I expect to see a way to add a new need. | Pass | BF; 10/30/2023 | Pass | CW; 11/13
| Given I am a Manager when I view my cupboard I expect to see a way to edit a need. | Pass | BF; 10/30/2023 | Pass | CW; 11/13
| Given I am a Manager when I add/edit a need I expect to see the needs information as modifiable data. | Pass | BF; 10/30/2023 | Pass | CW; 11/13
| Given I have added/edited a need when I view my cupboard then I expect to see the new/updated need. | Pass | KC; 10/30/2023 | Pass | NZ; 11/13
| Given I have added/edited a need when a Helper browses needs then I expect the Helper to see the added/edited need. | Pass | KC; 10/30/2023 | Pass | NZ; 11/13
As a Helper I want to view my notifications inbox so that I can see all messages in my inbox. | Given I have logged in when I am a Helper then I expect to see a way to access my notifications. |  |  | Pass | BF; 11/13/2023
| Given I am a helper when I view my notifications then I expect to see my inbox of messages. |  |  | Pass | BF; 11/13/2023
| Given I am viewing my inbox when I see a notification then I expect a way to tell from which need the notification was sent. |  |  | Pass | BF; 11/13/2023
As a Helper I want to clear a message from my inbox so that I don’t see it in my inbox anymore. | Given I am viewing my notifications inbox when logged in as a Helper then I expect a way to delete a message in my inbox. |  |  | Pass | BF; 11/13/2023
| Given I am viewing my inbox when I have deleted a message then I expect to not see the deleted message in my inbox. |  |  | Pass | BF; 11/13/2023
As a Helper I want to subscribe/unsubscribe button when viewing needs so that I can control what needs I receive notifications about. | Given I am a Helper when I browse needs then I expect a way to subscribe/unsubscribe from needs notifications. |  |  | Pass | BF; 11/13/2023
| Given I am a Helper when I subscribe to a need then I expect to start receiving notifications about it. |  |  | Pass | BF; 11/13/2023
| Given I am a Helper when I unsubscribe from a need then I expect to stop receiving notifications about it. |  |  | Pass | BF; 11/13/2023
As a Helper I want to be able to search for a need so that I can find specific needs I want to add to my cart. | Given I am a user when I am viewing the cupboard then I expect to see a search bar. |  |  | Pass | RL; 11/19/2023
| Given I have put text in the search bar when I press the submit button then I expect the needs list should only show the needs that meet match my text. |  |  | Pass | RL; 11/19/2023
| Given I have put no text in the bar when I press the submit button then I expect the see the list of all needs, unfiltered. |  |  | Pass | RL; 11/19/2023
As a Manager I want to push a notification regarding a need so that helpers subscribed to the need can see the message. | Given I am a manager when I see needs in my cupboard then I expect a button to push a notification. |  |  | Pass | MF; 11/19
| Given I have a need selected when I attempt to push a notification then I expect to be asked for a message to send. |  |  | Pass | MF; 11/19
| Given I have provided a message when I push a notification then I expect it to show in subscribers' inbox. |  |  | Pass | MF; 11/19